## Sheet1
Quiz for Success Project Timline
Sl. No. | Name of Module | Comments | Status
1 | Registration | Users can register | OK
2 | Login | Login to system | OK
3 | Parent Category of Question | Category | OK
4 | Sub Category for Question | Sub Category | Not OK | May not be implemented
5 | Question Creation | Questions | OK
6 | Adding Options to Questions | Options | OK
7 | Quiz Parent Category | Quiz Category | OK
8 | Quiz Parent Sub Category | Quiz Sub Category | OK
9 | Quiz Creation | Add Quizes | OK
10 | Leaderboard Display |  | Not OK
11 | Search |  | Partially
12 | Adding Questions to Quiz |  | OK
13 | Adding Questions to Quiz | From existing Questions | Not OK
14 | Ads Area |  | OK
15 | Quiz Taking |  | OK
16 | Verifying Questions |  | Not OK
17 | Verifying Quiz |  | Not OK
18 | Publishing Quiz |  | Not OK
19 | Challenge Quiz |  | Not OK
20 | Editing Quiz |  | Not OK
21 | Editing Questions |  | Not OK
22 | Editing Choices |  | Not OK
23 | Editing Profile |  | Not OK
24 | Badges |  | Not OK
25 | Moderator |  | Not OK
26 | Travia | Take Travia | OK
27 | View Travia Score |  | OK